## Sheet1
SOC Schedule for Bertjan, Kpilot, 2007

	From	To	Focus
	May 28: Students begin coding for their GSoC projects; Google begins issuing initial student payments
Week 01	May 28, 2007	Jun 2, 2007	Write Use Case documentation of all conduit flows
Week 02	Jun 4, 2007	Jun 9, 2007	Review and revise Use Case documentation with mentor
Week 03	Jun 11, 2007	Jun 16, 2007	Create Sequence and Class Diagrams from Use Case documentation for all conduit flows.
Week 04	Jun 18, 2007	Jun 23, 2007	Review and revise Sequence and Class Diagrams with mentor. All flows and methods should be in SQDs.
Week 05	Jun 25, 2007	Jun 30, 2007	Review all design documentation to date. Ensure completeness and correctness. Aim for no changes to design after this. If all is complete and signed off, begin writing C++ code for base conduit classes.
Week 06	Jul 2, 2007	Jul 7, 2007	Write C++ code for base conduit classes
	July 9: Students upload code to code.google.com/hosting; mentors begin mid-term evaluations
Week 07	Jul 9, 2007	Jul 14, 2007	Do code review with mentor on base conduit code. Make any necessary corrections. Complete base classes.
	July 16: Mid-term evaluation deadline; Google begins issuing mid-term student payments
Week 08	Jul 16, 2007	Jul 21, 2007	Investigate, review with mentor, decide on whether to use base conduit classes for new or existing conduit. Plan approach. Review with mentor. Ensure no misses between needed work and design of base conduit code.
Week 09	Jul 23, 2007	Jul 28, 2007	Code concrete implementation of base conduit code.
Week 10	Jul 30, 2007	Aug 4, 2007	Continue concrete implementation of base conduit code. Begin creating test cases and cppunit classes for easy testability of conduit.
Week 11	Aug 6, 2007	Aug 11, 2007	Code review with mentor on new/updated conduit code. Make any necessary corrections. Complete conduit coding and test cases.
Week 12	Aug 13, 2007	Aug 18, 2007	Test and debug conduit code. Make necessary changes. Update test cases and cppunit classes.
	August 20: Students upload code to code.google.com/hosting; mentors begin final evaluations; students begin final program evaluations
Week 13	Aug 20, 2007	Aug 25, 2007	Review deliverables, code, progress with mentor. Discuss any final wrap-up issues and resolve them. Continue testing and debugging of conduit code. Ensure code documentation is up to date, correct, and as complete as possible.
	August 31: Final evaluation deadline; Google begins issuing student and mentoring organization payments
Week 14	Aug 27, 2007	Sep 1, 2007	Final review of all work and deliverables. Finish debugging, testing, writing of test cases.